## query
Title | Description | Category | Progress | Priority | Due date | Start date | Completion Date | Assigned to | Notes | Item Type | Path
Literature Survey on SCM | Conducted Literature survey on Hospital Supply Chain Management | Research | Completed | Medium | 2023-01-12 | 2023-01-11 | 2023-01-12 | Konica Saxena;#1042;#Shubham Chaudhari;#1040;#Shubham Mhaske;#1041;#Uma Maheswari K;#243;#Sachin S Anand;#1039 |  | Item | sites/D-TAS/Lists/Spend Analytics Dashboard
Literature Survey on Spend Analytics | Conducted literature survey on existing Spend Analytics Dashboards and in general. | Research | Completed | Medium | 2023-01-13 | 2023-01-12 | 2023-01-13 | Konica Saxena;#1042;#Shubham Chaudhari;#1040;#Shubham Mhaske;#1041;#Uma Maheswari K;#243;#Sachin S Anand;#1039 |  | Item | sites/D-TAS/Lists/Spend Analytics Dashboard
Public dataset discovery | Research on publicly available datasets on Supply Chain and Spend analytics | Research | Completed | Medium | 2023-01-14 | 2023-01-12 | 2023-01-14 | Konica Saxena;#1042;#Shubham Chaudhari;#1040;#Shubham Mhaske;#1041;#Uma Maheswari K;#243;#Sachin S Anand;#1039 |  | Item | sites/D-TAS/Lists/Spend Analytics Dashboard
Data Synthesis based on Individual Schemas | Data Synthesis based on Individual Schemas provided by the domain expert. Data were generated using a web based tool called Mockaroo. | Design;#Engineering | Completed | High | 2023-01-18 | 2023-01-16 | 2023-01-17 | Shubham Mhaske;#1041;#Uma Maheswari K;#243 |  | Item | sites/D-TAS/Lists/Spend Analytics Dashboard
Master csv creation | Creation of Master CSV file by doing SQL joins | Engineering;#Design | Completed | High | 2023-01-19 | 2023-01-17 | 2023-01-18 | Shubham Mhaske;#1041;#Uma Maheswari K;#243 |  | Item | sites/D-TAS/Lists/Spend Analytics Dashboard
Fine tuning of Master CSV | Master CSV were fine tuned to meet the requirements of the POC | Engineering | Completed | High | 2023-01-19 | 2023-01-18 | 2023-01-19 | Shubham Mhaske;#1041;#Uma Maheswari K;#243 |  | Item | sites/D-TAS/Lists/Spend Analytics Dashboard
Whiz portal access & project creation | Creating whiz profiles and projects | Engineering | Completed | Medium | 2023-01-24 | 2023-01-20 | 2023-01-24 | Konica Saxena;#1042;#Shubham Chaudhari;#1040 |  | Item | sites/D-TAS/Lists/Spend Analytics Dashboard
Data Dictionary creation | Data Dictionary creation for the NLP model of Whiz | Design;#Engineering | Completed | High | 2023-01-26 | 2023-01-23 | 2023-01-25 | Neha Salunkhe;#1043 |  | Item | sites/D-TAS/Lists/Spend Analytics Dashboard
Dashboard pins generation | Generating the different pins for dashboard | Engineering | Completed | High | 2023-02-07 | 2023-02-01 | 2023-02-07 | Konica Saxena;#1042;#Shubham Chaudhari;#1040;#Uma Maheswari K;#243;#Sachin S Anand;#1039;#Shubham Mhaske;#1041 |  | Item | sites/D-TAS/Lists/Spend Analytics Dashboard
Dashboard front-end refinement | Dashboard front-end refinement | Engineering | Completed | High | 2023-02-23 | 2023-02-20 | 2022-12-05 | Konica Saxena;#1042;#Shubham Chaudhari;#1040;#Shubham Mhaske;#1041;#Uma Maheswari K;#243;#Sachin S Anand;#1039 |  | Item | sites/D-TAS/Lists/Spend Analytics Dashboard
Dashboard back-end refinement | Dashboard back-end refinement | Engineering | Completed | High | 2023-02-22 | 2023-02-20 | 2023-02-21 | Neha Salunkhe;#1043 |  | Item | sites/D-TAS/Lists/Spend Analytics Dashboard